## Instructions
SN | Steps
1 | Define the Release Theme in 'User_Story_Map_Board' Tab
2 | Identify the set of User activities in horizontal blocks
3 | Create / Define the user stories under each epic block
4 | Identify / Set the release version and also the sprint timeline
5 | Shuffle the user stories for corresponding EPICs based on priority such that it adds value to production
6 | Complete defining all the user stories, priority of story execution in each sprints
7 | Update the 'Agile Release Plan' sheet with all User stories and dates
8 | Create the user stories in 'Agile User Story' Tab with details i.e. As a format and Given When Then while defining the acceptance criteria

## User_Story_Map_Board
|  | Epic 1 |  | Epic 2 |  | Epic 3 |  | Epic 4 |  | Epic 5 |  | Epic 6 |  | Epic 7 |  | Epic 8
the BACKBONE | Registeration |  | Login |  | Event |  | Profile |  | Manage Users |  | Manage Class |  | Assignments |  | Study Materials
|  |  | US01: As an admin I want to login so that I could access admin dashboard |  | US02: As an admin I want to add and view events so that I can notify the teacher and students |  |  |  | US05: As a admin I want to view account request so that I can approve the account request. |  | US08: As an admin I want to manage the faculty so that the I can update information of the faculty
FLESH on the backbone
[5 empty] | US03: As an admin I want to update events so that I can upload new events |  |  |  | US06: As an admin I want to confirm account request so that I can allow the users to acces the system |  | US09: As an admin I want to manage the sections so that I can update the sections
Sprint / Iteration 1 (08/09/2019 - 15/09/2019) |  |  |  |  | US04: As an admin I want to delete events so that I can wipe out old events |  |  |  | US07: As an admin I want to forbid users account request so that I can limit the users access to the system
SEQUENCE
Version 1.0
| US10: As a teacher I want to register so that I can get approval from admin to access the system |  | US11: As a teacher I want to login so that I can access teacher dashboard |  | US12: As a teacher I want to view event so that I can get events information details. |  | US13: As a teacher I want to view and update my profile so that I can change my profile information |  | US14: As an admin I want to view and update users details so that I can change their information |  |  |  | US16: As a teacher I want to add the assignments so that I can upload new asssignment |  | US19: As a teacher I want to add study materials so that I can help them in their academic study
[9 empty] | US15: As an admin I want to delete users so that I can limit users enrollment in the system. |  |  |  | US17: As a teacher I want to update the assignmnets so that I can change asssignment details |  | US20: As a teacher I want to update study materials so that I can change the uploaded study materials
Sprint / Iteration 2 2(09/09/2019 - 16/09/2019) | [12 empty] | US18: As a teacher I want to delete the assignmnets so that I can add new assignments |  | US21: As a teacher I want to delete study materials so that I can free space for other study materials
Version 2.0
| US22: As a student I want to register so that I can get approval from admin to access the system |  | US23: As a student I want to login so that I could acces to student dashboard system. |  | US24: As a student I want to view event so that I can know about upcoming events. |  | US25: As a student I want to view and update the profile so that I can change my academic information | [5 empty] | US26: As a teacher I want to download student assignmnets by section wise so that I can grade students assignments |  | US31:As a student I want to view study material so that I can get access to various notes and documents.
[13 empty] | US27:As a student I want to view my assignments so that I can get notify about my assignment. |  | US32:As a student I want to download study material so that I can have a copy of notes and documents.
Sprint / Iteration 3 (16/09/2019 - 23/09/2019) | [12 empty] | US28:As a student I want to upload my assignments so that I can submit my asssignment for grading
Version 3.0
US29:As a student I want to download my assignments so that I can have a copy of my asssignment.
US30:As a student I want to view history of my assignments so that I can view my previous assignment information.
Sprint / Iteration 4 (23/09/2019 - 30/09/2019)
Version 4.0
Sprint / Iteration 5 (30/09/2019 - 07/10/2019)
Version 5.0
RELEASE THEME : LEARNING MANAGEMENT SYSTEM
FEATURE CRITICALITY
Legend : US - User Story
Note on C8: Deepak: Highlevel Activities a user will accomplish while using the product
Note on C11: Deepak: Under each activity on the backbone we add use stories that support the activity
Note on C17: Deepak: What the team will aim to deliver and when
Note on C18: Deepak: First Release of small increments
Note on C26: Deepak: Second Release of small increments
Note on C35: Deepak: Third Release of small increments
Note on C47: Deepak: Fourth Release of small increments
Note on C56: Deepak: Fifth Release of final increments

## Agile Release Plan
AGILE RELEASE PLAN
AT RISK | SPRINT | USER STORY NAME | FEATURE TYPE | START | FINISH | DURATION | STORY POINTS | STATUS | RELEASE DATE | GOAL
| 1 | User Story 1 | Functionality | 2019-08-09 | 2019-09-09 | 1 | 2 | Released | 15/9/2019
| 1 | User Story 2 | Functionality | 2019-09-09 | 2019-10-09 | 1 | 1 | Released | 2022-07-24 |  | This section is for the drop-down list
| 1 | User Story 3 | Functionality | 2019-09-09 | 2019-10-09 | 1 | 2 | Ongoing | 2022-08-01 |  | Planned
| 1 | User Story 4 | Functionality | 2019-10-09 | 2019-11-09 | 1 | 1 | Planned | 2022-08-08 |  | Ongoing
| 1 | User Story 5 | Functionality | 2019-10-09 | 2019-11-09 | 1 | 1 | Released | 2022-07-12 |  | Released
| 1 | User Story 6 | Functionality | 2019-11-09 | 2019-12-09 | 1 | 2 | Released | 2022-07-24
| 1 | User Story 7 | Functionality | 2019-11-09 | 2019-12-09 | 1 | 1 | Ongoing | 2022-08-01
| 1 | User Story 8 | Functionality | 2019-12-09 | 13/9/2019 | 1 | 1 | Planned | 2022-08-08
| 1 | User Story 9 | Functionality | 2019-12-09 | 13/9/2019 | 1 | 1
| 2 | User Story 10 | Functionality | 13/9/2019 | 14/9/2019 | 1 | 3
| 2 | User Story 11 | Functionality | 13/9/2019 | 14/9/2019 | 1 | 3
| 2 | User Story 12 | Functionality
| 2 | User Story 13 | Functionality
| 2 | User Story 14 | Functionality
| 2 | User Story 15 | Functionality
| 2 | User Story 16 | Functionality |  |  | 0
| 2 | User Story 17 | Functionality |  |  | 0
| 2 | User Story 18 | Functionality |  |  | 0
| 2 | User Story 19 | Functionality |  |  | 0
| 2 | User Story 20 | Functionality |  |  | 0
| 2 | User Story 21 | Functionality |  |  | 0
| 3 | User Story 22 | Functionality |  |  | 0
| 3 | User Story 23 | Functionality |  |  | 0
| 3 | User Story 24 | Functionality |  |  | 0
| 3 | User Story 25 | Functionality |  |  | 0
| 3 | User Story 26 | Functionality |  |  | 0
| 3 | User Story 27 | Functionality |  |  | 0
| 3 | User Story 28 | Functionality |  |  | 0
| 3 | User Story 29 | Functionality |  |  | 0
| 3 | User Story 30 | Functionality |  |  | 0
| 3 | User Story 31 | Functionality |  |  | 0
| 3 | User Story 32 | Functionality |  |  | 0
0
0

## Agile User Story
AGILE USER STORY
Feature ID | USER STORY ID | PRIORITY | AS A <type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal> | FINAL STORY
F1 | US01 | High | Admin | login | access admin dashboard |  | This section is for the drop-down list
| US02 | Medium | Admin | add and view events | notify teacher and student about the events |  | Medium
| US03 | Medium | Admin | update event | upload information about new events |  | Low
| US04 | Medium | Admin | delete event | remove old events
| US05 | High | Admin | view users account request | can decide user request
| US06 | High | Admin | accept users account request | change users roles
| US07 | Medium | Admin | delete users account request | limit the users access to the system
| US08 | High | Admin | manage faculty | change faculty information
| US09 | High | Admin | manage sections | change information about the sections
F2 | US10 | High | Teacher | Register | get approval from admin to access the system
| US11 | High | Teacher | Login | access teacher dashboard
| US12 | Medium | Teacher | view events | get events information details
| US13 | Medium | Teacher | view and update profile | change profle information
| US14 | High | Admin | view and update user details | change users information
| US15 | Medium | Admin | delete user details | limit users enrollment in the system
| US16 | High | Teacher | Add assignment | upload new assignment
| US17 | High | Teacher | update the assignments | get assignment details
| US18 | Medium | Teacher | delete assignment | add new assignment
| US19 | High | Teacher | add study materials | help them in their acedemic study
| US20 | High | Teacher | update study materials | change the uploaded study materials
| US21 | Medium | Teacher | delete study materials | free space for other study materials
F3 | US22 | High | Student | register | get approval from admin to access the system
| US23 | High | Student | Login | acces to student dashboard system
| US24 | Medium | Student | view events | know about upcoming events
| US25 | Low | Student | update profile | change my academic information
| US26 | High | Teacher | download student assignment | grade student assignments
| US27 | Medium | Student | view assignment | get notify about my assignment
| US28 | High | Student | upload assignment | submit my asssignment for grading
| US29 | High | Student | download assignment | have a copy of my asssignment
| US30 | Low | Student | view history | view my previous assignment information
| US31 | Medium | Student | view study material | get access to various notes and documents
| US32 | High | Student | download study material | have a copy of notes and documents

## Agile Sprint_1 Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | SPRINT REVIEW
User Story #1 | 2 |  | In Progress
Task Developer1 |  | Unish Rijal | To Do | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task Developer 2 |  | Himanchal Malla |  | 3 | 2 | 0 | 0 | 0 | 0 | 0
Task Developer3 |  | Roshan Shah |  | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Task TestingTDD |  | Amar Kumar Mahato |  | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Task TestingBDD |  | Amit Chand |  | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0
User Story #2 | 1 |  | To Do
Task Developer1 |  | Unish Rijal |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
Task Developer 2 |  | Himanchal Malla |  | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
Task Developer 3 |  | Roshan Shah |  | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
Task Testing TDD |  | Amar Kumar Mahato |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Task Testing BDD |  | Amit Chand |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
User Story #3 | 2 |  | To Do
Task Developer1 |  | Unish Rijal |  | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Task Developer2 |  | Himanchal Malla |  | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Task Developer3 |  | Roshan Shah |  | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Task Testing TDD |  | Amar Kumar Mahato |  | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Task Testing BDD |  | Amit Chand |  | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 0
User Story #4 | 1 |  | To Do
Task Developer1 |  | Unish Rijal |  | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Task Developer2 |  | Himanchal Malla |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Task Developer3 |  | Roshan Shah |  | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Task TestingTDD |  | Amar Kumar Mahato |  | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0
Task TestingBDD |  | Amit Chand |  | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0
User Story #5 | 1 |  | To Do
Task Developer1 |  | Unish Rijal |  | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Task Developer2 |  | Himanchal Malla |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Task Developer3 |  | Roshan Shah |  | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Task TestingTDD |  | Amar Kumar Mahato |  | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0
Task TestingBDD |  | Amit Chand |  | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0
User Story #6 | 2 |  | To Do
Task Developer1 |  | Unish Rijal |  | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0
Task Developer2 |  | Himanchal Malla |  | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 0
Task Developer3 |  | Roshan Shah |  | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0
Task TestingTDD |  | Amar Kumar Mahato |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0
Task TestingBDD |  | Amit Chand |  | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0
User Story #7 | 1 |  | To Do
Task Developer1 |  | Unish Rijal |  | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Task Developer2 |  | Himanchal Malla |  | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task Developer3 |  | Roshan Shah |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Task TestingTDD |  | Amar Kumar Mahato |  | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Task TestingBDD |  | Amit Chand |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
User Story #8 | 1 |  | To Do
Task Developer1 |  | Unish Rijal |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
Task Developer2 |  | Himanchal Malla |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
Task Developer3 |  | Roshan Shah |  | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0
Task TestingTDD |  | Amar Kumar Mahato |  | 2.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Task TestingBDD |  | Amit Chand |  | 2.5 | 0 | 1 | 0 | 0 | 0 | 0 | 0
User Story #9 | 1 |  | To Do
Task Developer1 |  | Unish Rijal |  | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Task Developer2 |  | Himanchal Malla |  | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Task Developer3 |  | Roshan Shah |  | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Task TestingTDD |  | Amar Kumar Mahato |  | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0
Task TestingBDD |  | Amit Chand |  | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0
TOTAL |  |  |  | 96 | 27 | 15 | 23 | 10 | 6 | 16 | 0
IDEAL |  |  |  | 78 | 7.8 | -4.2 | 3.8 | -9.2 | -13.2 |  | -19.2
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_2_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8 |  | In Progress
Task |  |  | To Do | 7 | 5 | 2 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1 |  | To Do
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5 |  | To Do
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8 |  | To Do
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3 |  | To Do
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 20 | 58 | 41 | 20 | 18 | 14
IDEAL |  |  |  | 78 | 4.4 | 42.4 | 25.4 | 4.4 | 2.4 | -1.6
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_3_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8 |  | In Progress
Task |  |  | To Do | 7 | 5 | 2 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1 |  | To Do
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5 |  | To Do
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8 |  | To Do
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3 |  | To Do
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 20 | 58 | 41 | 20 | 18 | 14
IDEAL |  |  |  | 78 | 4.4 | 42.4 | 25.4 | 4.4 | 2.4 | -1.6
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_4_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8 |  | In Progress
Task |  |  | To Do | 7 | 5 | 2 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1 |  | To Do
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5 |  | To Do
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8 |  | To Do
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3 |  | To Do
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 20 | 58 | 41 | 20 | 18 | 14
IDEAL |  |  |  | 78 | 4.4 | 42.4 | 25.4 | 4.4 | 2.4 | -1.6
| Remaining Effort | 7
Ideal Trend

## Agile Sprint_5_Backlog
AGILE SPRINT BACKLOG WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 | 8 |  | In Progress
Task |  |  | To Do | 7 | 5 | 2 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 0 | 0
User Story #2 | 1 |  | To Do
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 | 0 | 1
User Story #3 | 5 |  | To Do
Task |  |  |  | 8 | 6 | 0 | 0 | 0 | 0 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 3
User Story #4 | 8 |  | To Do
Task |  |  |  | 9 | 4 | 2 | 2 | 1 | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
User Story #5 | 3 |  | To Do
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
TOTAL |  |  |  | 78 | 20 | 58 | 41 | 20 | 18 | 14
IDEAL |  |  |  | 78 | 4.4 | 42.4 | 25.4 | 4.4 | 2.4 | -1.6
| Remaining Effort | 7
Ideal Trend

## Sprint_Review_Retro
Sprint | What worked Well | What didn’t work well or could use as improvement | Individual Point that led / could lead to happiness
1
2